## Sheet1
Project Charter
| GENERAL PROJECT INFORMATION | CHARTER DATE: March 2023
| Project Name | SHOT-POS: A Point of Sale System for SHOT Café
| Project Sponsor | SHOT Cafe
| Project Manager | John Louie Campos
| Expected Start Date | 2023-05-23
| Expected Completion Date | 2023-07-01
PROJECT DETAILS
| Project Description | SHOT Cafe, a local coffee shop situated in Mandaluyong City, is taking steps to improve its efficiency and customer service by introducing a contemporary Point of Sale (POS) system. Presently, the coffee shop relies on traditional manual order-taking methods, which can be time-consuming and prone to mistakes. The management of SHOT Cafe acknowledges the necessity for an automated and efficient system to optimize their operations and ensure a more satisfying experience for their patrons. SHOT-POS, the suggested point-of-sale system, aims to serve as a holistic answer to the coffee shop's requirements. By incorporating a range of capabilities and features, it will improve customer satisfaction, streamline transactions, efficiently handle inventory, and offer valuable business insights.
| Key Requirements | The team will deliver these usable features: 1. System front-end – working design 2. Saves sale transaction 3. Editable menu 4. Database management 5. Preview of previous sales track
| Expected Benefits | • Customer satisfaction • Improve efficiency, accuracy, and production • Improve product management • Optimize workflows • Possible higher profitability • Possible to lower expenses • Increased market competitiveness • More sales
| Expected Cost & Resources | 1. Human Resources: • Project Manager • Team Members 2. Materials and Equipment: • Computers/Laptops • Internet Connection • Software Tools 3. Communication Tools: • Video Conferencing using Discord • Google Documents
| Estimated Milestones | Week 1 (2nd week of May) - Planning / project initiation Week 2 (3rd week of May) - Requirements Gathering and Analysis Week 3 (4th week of May) - System Design Week 4 & 5 (Last week of May and first week of June) – Development Week 6 & 7 (2nd & 3rd week of June) – Testing Week 8 (Last week of June) – Deployment Week 9 (1st week of July) - Project Closure
0 | Project Team | Project Manager: Campos, John Louie Member: Mejia, Juan Paulo Member: Rapiza, Leinard Member: Tolentino, John Cedrick
| Stakeholders | 1. Project Sponsor: SHOT Cafe 2. Project Manager: Campos, John Louie 3. Project Team Members: Mejia, Juan Paulo Rapiza, Leinard Tolentino, John Cedrick 4. Sponsor’s customers
| Overall Project Risk | • Technical risk o Maintenance • Schedule risk o Time management
| Project Exit Criteria | • The over all system is functional and operational. • The system's user-friendly interface design enhances ease of use. • The menu editing feature of the system is fully functional. • The system effectively tracks and records sales transactions.